## Slide 1
[ INTERNAL USE ONLY ]
PROJECT CHARTER
F.lli Ferrari Market Strategy
F.LLI FERRARI MARKET STRATEGY · PROJECT CHARTER
01 / 01
PROJECT NAME
F.lli Ferrari Market Strategy
BACKGROUND
Triatra distributes F.lli Ferrari truck-mounted knuckle boom cranes in Indonesia. From Jan 2023 to Aug 2026, Indonesia imported 638 knuckle boom cranes; Medium and Heavy cranes (above 25 tm) are 41% of units but 64% of import value, led by Sany Palfinger and Palfinger. F.lli Ferrari is cheaper than European rivals in five tm classes, but costs more than Chinese brands. This project is initiated to give a structured assessment of where F.lli Ferrari can compete, which cranes to stock and how to position them, so the F.lli Ferrari line grows on a sound, data-based footing.
OBJECTIVES
1. Map Indonesia's knuckle boom crane market by Max Lifting Moment (tm) class, brand and model
2. Compare F.lli Ferrari head to head with every competitor model on price, size and features
3. Define which F.lli Ferrari cranes Triatra should stock and how to position them
PROJECT SCOPE
F.LLI FERRARI CRANES, MEDIUM AND HEAVY CLASS (> 25 tm)
1. Market size & brand leaders
2. Price comparison by 5-tm class
3. F.lli Ferrari crane advantage
4. Stock & positioning strategy
5. Implementation timeline & sales plan
KPI / METRIC
TARGET
1. Market map by tm class, brand and model (2023 – 2026)
2. Competitor price and specification benchmark
3. List of F.lli Ferrari cranes that win head to head
4. Stock recommendation per tm class
5. Implementation timeline and sales plan
Delivered the F.lli Ferrari market strategy in March 2027
SUPPORT REQUIRED
Marketing and Sales; United Tractors Pandu Engineering (UTPE); F.lli Ferrari Italia
PROJECT TIMEFRAME
Activity
2026
2027
Jun
Jul
Aug
Sep
Oct
Nov
Dec
Jan
Feb
Mar
Planning – Framework
Observation, Study, and Review
Analysis and Formulation
Reporting and Evaluation
BENEFIT OF PROJECT
Give Triatra a clear, data-based basis to choose which F.lli Ferrari cranes to stock, and to target the tm classes and customers where F.lli Ferrari wins on price and quality.
PROJECT TEAM
Executive Sponsor
Advisor
Coordinator
Project Lead
Team Member
: Ricardo Tanada
: Ricardo Tanada
: Ignatius Indrawan
: Tiberias Krisgaharu Simu
: Yohannes Eurico Christanto, Muhammad Fawwaz Jauharin
PROJECT APPROVAL
Lead
Date:
Tiberias Krisgaharu Simu
Coordinator
Date:
Ignatius Indrawan
Advisor
Date:
Ricardo Tanada
Executive Sponsor
Date:
Ricardo Tanada